## Roadmap
ID | Priority | Status | Are | Title | Description | Source | Created On
RM-001 | P0 | Done | Compositor | Fix halo around pasted/restored regions | Investigate mask feather/dilation, colorspace/range mismatch, resize interpolation; match LADA paste/blend behavior. | Jan2026-26.md; Jan2026-27.md | 2026-01-27
RM-002 | P0 | Done | Detection/Preprocess | Eliminate YOLO CPU hop | Move letterbox/preprocess to torch on GPU/XPU; keep frames and YOLO outputs on-device (no CPU uint8/NumPy). | Dec-19.md:590; Dec-19.md:304 | 2026-01-27
RM-003 | P0 | Done | Video I/O | Fix remux/mux timestamps (Duration N/A) | Ensure output container has valid duration/PTS/DTS; handle VFR; verify via ffprobe frame pkt_pts_time/pkt_duration_time. | Dec-19.md:3254; Dec-21.md | 2026-01-27
RM-004 | P0 |  | Pipeline | Early passthrough when no detections | If det=0 and no active scenes, encode original frame immediately (avoid storing full-res GPU frame) | Dec-26.md:4025 | 2026-01-27
RM-005 | P1 |  | Detection | Tiled detection for 4K+ sources | Add overlapping tiling path for YOLO; merge boxes with NMS/union; reduce missed small mosaics in high-res sources. | Nov-10.md:506; Nov-10.md:613 | 2026-01-27
RM-006 | P1 |  | Detection/Mask | GPU mask postproc (dilate/feather/gain) | Implement dilation/feathering/gain entirely on GPU/XPU (torch); reduce CPU mask ops and match LADA blend strategy. | Nov-10.md:506 | 2026-01-27
RM-007 | P1 |  | Restoration | ROI-cropped restoration to save compute | Optionally crop to ROI bbox (+context), run restoration on crop, paste back; reduce VRAM/compute for small mosaics. | Nov-10.md:512 | 2026-01-27
RM-008 | P1 |  | Detection Tuning | Dynamic imgsz by input resolution | Auto imgsz heuristic (e.g., 640 for 1080p, 960 for higher-res) to improve detection quality/perf balance. | Dec-26.md:1659; TODO-17 | 2026-01-27
RM-009 | P1 |  | Detection Robustness | Investigate intermittent missed ROI detections | Compare padding/letterbox parity, conf threshold, imgsz, fp16/precision, ROI dilation/union; add logging to isolate frames. | TODO-19 | 2026-01-27
RM-010 | P1 |  | ROI Tracking | Control ROI unions vs per-box | Add option to control union/merge strategy and padding rounding; mitigate ROI flicker and scene membership drift. | Dec-26.md; TODO list | 2026-01-27
RM-011 | P1 |  | Video I/O | NVDEC prefetch N/N+1 (2-batch) | Decode next batch while current batch runs detection/restoration to reduce GPU idle gaps and keep NVDEC busy. | Jan2026-23.md thread notes | 2026-01-27
RM-012 | P2 |  | CLI/UX | Custom ffmpeg decoder/encoder args | Allow user-specified ffmpeg input and output options; ensure input opts placed before -i; validate and surface stderr. | Existing memory | 2026-01-27
RM-013 | P2 |  | Metrics | Better timing + print around remux | Add prints around remux and per-stage timing so perf regressions are visible; include decode/det/rest/encode durations. | Jan2026-23.md:2234 | 2026-01-27
RM-014 | P2 |  | VR/SBS | Parallel SBS processing | Explore running left/right eye restoration concurrently (if VRAM allows) and/or overlap pipeline stages. | Dec-26.md; Dec-31.md | 2026-01-27
RM-015 | P0 |  | VR/SBS | VR pre-projection options for detection | Optional fisheye/v360 transforms to improve detector performance on VR projections; keep fast path. | Zelefans notes | 2026-01-27
RM-016 | P3 |  | Packaging | Inference-only model graph port | Port/verify inference-only graph (TSA/PCD/residual) to minimize overhead; ensure weights load without training deps. | Oct-28.md:410 | 2026-01-27
RM-017 | P3 |  | Diagnostics | Startup banner: file version + config echo | Print build/version hash and resolved config at startup for reproducibility. | Nov-03.md:2528 | 2026-01-27
RM-018 | P3 |  | UX | Progress indicators | Add progress bars / throughput readout; keep logs clean under MF_DEBUG/GR_DEBUG. | Nov-03.md:1040 | 2026-01-27
RM-019 | P0 |  | Detection | Inference-Letterbox | Keep mask postproc + compositor ops on-device (torch); eliminate unnecessary CPU conversions. | GS/chatGPT | 2026-01-27
RM-020 | P1 |  | Debug | Standardize env-var debug controls | Keep and standardize env-var driven debug hooks across modules (dump frames/masks/boxes). | Halo investigation; mask/alpha/overlay dumps; unify toggles | 2026-01-29
RM-021 | P1 |  | Pipeline | Avoid pinned min_active_start | Implement rolling clip finalization so long active scenes don’t pin min_active_start; let safe_before advance and frames drain.Add per-scene “emitted watermark” (safe_emitted_until) so safe_before can move forward during long scenes; reduce buffering. | Claude suggestion merge | 2026-02-15
RM-022 | P0 |  | Pipeline | Bound FrameStore growth (cap + emergency ceiling) | Add FrameStore max_frames with backpressure; when blocked by active scene (safe_before pinned)- temporarily raise cap to bounded emergency ceiling; otherwise block/retry (no runaway decode). | ClaudeParityAnalysis.md:11.3; patch CHANGE-2 followup | 2026-02-15
RM-023 | P1 |  | CLI/UX | Add strict LADA parity preset (disable stabilization) | Provide a one-flag preset (or config profile) that sets crop_quant_px=0, crop_sticky=False, match_pad_px=0 (and any other stabilization extras) for apples-to-apples parity testing. | ClaudeParityAnalysis.md:11.2 #1; 7.1 #1-2 | 2026-02-15
RM-024 | P1 |  | Restoration | Add big-ROI quality warning + clip_size option | Track downscale ratio (roi_area vs clip_size^2) and warn when restoration heavily downsamples; allow clip_size=512 (or configurable) when VRAM allows. | ClaudeParityAnalysis.md:8.1 | 2026-02-15
RM-025 | P2 |  | Restoration | Tile very large ROIs for restoration | For ROIs covering large % of frame, split into overlapping tiles (e.g., 256x256), restore each, then feather-blend tiles back to avoid extreme downscale artifacts. | ClaudeParityAnalysis.md:8.1 | 2026-02-15
RM-026 | P0 |  | Video I/O | Robust PTS/timebase handling (VFR-safe mode) | Plumb per-frame PTS end-to-end and infer timebase (ns/us/90k/etc.) before deriving fps; if VFR detected, warn and choose explicit strategy (CFR by avg fps vs true VFR container path). | ClaudeParityAnalysis.md:10.3; 11.2 #5; existing RM-003 related | 2026-02-15
RM-027 | P2 |  | Performance | Overlap detection and restoration with CUDA streams | Use separate CUDA streams (and events) to overlap YOLO and BasicVSR++ work where possible; profile to ensure net throughput gain without VRAM spikes. | ClaudeParityAnalysis.md:9.2 | 2026-02-15
RM-028 | P3 |  | Cleanup | Remove redundant double mask OR in _compute_crop | Eliminate the second seg_mask OR pass in _compute_crop (idempotent) to reduce clutter and avoid confusion in parity reviews. | ClaudeParityAnalysis.md:11.2 #4; 7.1 #4 | 2026-02-15
RM-029 | P3 |  | Testing | Test non-256 clip_size mapping in crop_box_to_target_v3 | Add a unit test (or quick harness) to verify crop_box_to_target_v3 target_hw mapping behaves correctly for clip_size != 256 / non-square targets. | ClaudeParityAnalysis.md:11.2 #3 | 2026-02-15
RM-030 | P0 | Done | Packaging | Build a packager for gRestorer - on Windows | Create one executable, with config outside of _internal, at the same level as gRestorer.exe | GS | 2026-02-17
RM-031 | P4 |  | Packaging | Build a packager for gRestorer - on Unix | Build packager for Unix | GS | 2026-02-17